## Sheet1
Discuss Monitor and review. Do we: | RAG | Action | Outcome | Resources | Completion date
Hold discussions with stakeholders on bullying and its definition | 1 | * Safe to Learn conference with student voice, parents from PTA and keys staff | * Agreed definition of bullying to put to staff/student body * Agreed anti bullying policy * Outline of 'Safe to learn' campaign | * time * £200, food
Keep a record of bullying incidents according to our agreed definition and anaylse it for patterns | 1 | * Relaunch incident recording system - possibly online? | * Simple system that is consistently used by all staff * Monthly review of data with actions | * time
Ask what makes an anti-bullying school | 1 | * Safe to learn conference with student voice, parents from PTA and keys staff * Discussion in departments * Discussion is SV | * Anti bullying charter and commitment that is know by all stakeholders | * time
Ensure that young people feel 'safe to learn' | 1 | * 'Safe to learn campaign', led by SV | * Increase in students feeling safe at school | * time * £50 for printing etc
Celebrate our successes and share these with parents | 1 | * Share in newletter and on website the progress and results made (e.g. taking photos of conference) | *Parents and pupils know that student safety is improving | * time
Support everyone to identify and respond? Do we:
Work with staff and agencies to identify all forms of prejudice driven bullying | 1 | * Staff CPD (led by ext agency?) identifying and tackling bullying * Dissemination and constant revisiting Safe to learn definition and charter | *All staff understand key types of prejudice and are robust in tackling these * Students perception is that we deal effectively with issues of prejudice | * allocation of CPD time * printing (£20)
Promote SEAL to reduce bullying | 1 | * SEAL work in forms/PSHE?? | * ??
Looked for all opportunities where bullying can be addressed (including curriculum, SV, peer support) | 2 | * Bring strands together to ensure consistent approach (prefects, ABC, Peer mentors, SV) * Depts identify at least one area in which they can tackle issues of bullying/prejudice | * Students and staff understand and can describe how the school tackles bullying * Students describe how the curriculum tackles bullying | *time
Create safe places for vulnerable studens AND train lunchtime staff ec to identify bullying and follow the schools policy | 2 | * Advertising of safe places to all students (assemblies, Safe to Learn cards) etc (SV funding?) * Training and review of lunch time staff | * All students can describe where to go if they feel unsafe * All lunchtime staff are consistently active in safeguarding students | *time *£200 printing
Ensure that children and young people are aware that all bullying concerns will be dealt with sensitively and effectively
Canvas students views re bullying and ensure that they know how to express their worries about bullying | 2 | * Canvas through big conversation and student survey (3 times a year) * Regular work through assemblies and form * Inclusion in contact books | * All students feel that they are listened to * All pupils can explain what they do if they are worried about bullying | * time
Ensure students are aware of the sanctions applied against bullying | 1 | * Regular discussion in form and assemblies * Posters, distribution of Safe to Learn policy | * All students can describe what the sanctions are | * time * printing (included above)
Involve students in anti bullying campaigns | 2 | * Safe to Learn conference * Student prefects etc. * form group assemblies | * All students can describe how students are involved in promoting 'Safe to Learn' | *time
Use peer support, peer counselling, peer meditation effectively | 2
Include helpline numbers in student planners, have an anti bullying notice board and in other wise bring anti bullying measures to students attention | 2 | * bring strands together as above | As above | *none
Involve student council | 3 | * Safe to learn conference * Big Conversation * Termly agenda item | * Student council can describe the impact that they have had | * none
Offer support to students who have been bullied | 2 | * Counselling(advertising and signposting * CPD for form tutors | * All students feel that they can access support
Ensure that parents/carers expression of bullying concerns have been taken seriously: Do
Parents know who to contact | 2 | * Letter sent to parents re 'Safe to learn' * Safe to Learn on website * Portable notice board up at parents evening * Contact point at all parents evenings * launch of parentdesk (see parentdesk.co.uk/hoo) | * All parents aware of who to contact * Parents see school as proactive in encouraging reporting of bullying * School can demonstrate how they dealt with all communications regarding bullying | *time *£250 display board and printing
Parents know complaints procedure | 1 | * Updating and dissemination of complaints procedure | * | *time * printing postal costs